## Title Page
Group Number: | 6 | Group Name: | MyKitchen | Sprint Number: | 3

## Product Backlog
Project Number | 6
Project Name: | MyKitchen
Description: | The all-in-one kitchen assistant. You can find recipes, plan meals, create shopping lists, and coordinate with roommates all from the same app! |  |  | PRODUCT BACKLOG
Team Members | Levi Carpenter, Akshay Patel, Erick Garcia, Noah Gillespie
Story # | Card Front | Card Back | Sprint Number | Priority | Assigned To | Comments | Estimated Size (Points) | Estimated Size (SML) | Estimated Size (Hours) | Estimated Velocity Per User Story
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | [7 empty] | (Estimated Size / Estimated Hours)
ST-1 | As a user, I want to register for a new account so that I can use the app | Registering new accounts | 3 | Priority: High | Levi | Completed in 3 |  | L | 9
ST-2 | As a user, I want to sign into my account so that I can use the app | Sign in to existing accounts | 3 | Priority: High | Levi | Completed in 3 |  | M | 5
ST-3 | As a cook, I want to be able to search for recipes so that I can try to cook new things | Search for online recipes | 3 | Priority: Medium | Levi | Started in sprint 2. Incomplete. Completed in 3 |  | L | 9
ST-4 | As a student, I want to be able to share my grocery list with my roomates so that splitting the bill is easier | Grocery list sharing | 4 | Priority: High | Noah | In progress. Completed in sprint 4 |  | M | 5
ST-5 | As a frequent home cook, I want the app to keep track of my pantry so that I am not buying ingredients I already own | Pantry section | 3 | Priority: High | AK | Completed in 3 |  | S | 2
ST-6 | As a student, I want to know what the total is going to be for my grocery trip | Price checking on items | N/A | Priority: Low | Noah | Not completed. Moved to future sprint. | 9 | S | 2
ST-7 | As a shopper, I want my ingredients to be grouped into types so that my shopping trip is more efficient | Grocery list grouping | 3 | Priority: High | Levi | Completed in 3 |  | M | 5
ST-8 | As a cook, I would like to be able to upload recipies to the app so that I can store my personal recipies in one place | Ability to upload recipies for personal use on the apps | 4 | Priority: Medium | Levi | Started in sprint 2. Incomplete. completed in sprint 4 |  | S | 2
ST-9 | As a college roomate I want to be able to join my roomate in a shared space to look at the groceries we are going to get this week | Ability for roomates to join groups | 3 | Priority: High | Noah | Started in sprint 2. Moved to sprint 4 |  | XL | 12
ST-10 | As a roommate, I would like to add an item to the grocery list for the house wide grocery list | Ability for roomates to add and edit grocery lists | 4 | Priority: High | Noah | Complete in sprint 4 |  | M | 5
ST-11 | As a late night worker, I want to see what meals I have planned for the week on my way home from work so that I will be able to more effeciently pick a meal | Meal viewer | 3 | Priority: High | Erick | Started in sprint 2. Incomplete. Completed in 3 |  | L | 9
ST-12 | As a home cook, I want to be able to manually add and remove items from my pantry so that the pantry section of the app is always accurate | Manual pantry additions / removal | 3 | Priority: Medium | AK | Completed in 3 |  | S | 2
ST-13 | As a roommate, I would like to share recipes with my other roommates so they can save the recipes they liked. | Recipe sharing | Next sprint | Priority: Low | Noah | In progress |  | M | 5
ST-14 | As a shopper, I want to be able to mark items off of my grocery list, so that I can keep track of what I have already picked up while shopping | Ingredient mark off | 4 | Priority: Medium | Levi | Completed in sprint 4 |  | S | 2
ST-15 | As a cook who plans meals for the week, I want to be able to mark off meals as I cook them so that I know what's left to cook | Mark off cooked meals in meal viewer | 4 | Priority: Medium | Erick | Completed in sprint 4 |  | S | 2
ST-16 | As a grocery store shopper, I want to know if a store is going to be out of a specific item. | Grocery store inventory check | N/A | Priority: Low | Noah | Not completed. Moved to future sprint. | 9 | S | 2
ST-17 | As a college student I want to be able to see what recipes I can make given the ingredients I have, even when missing one or two. | Lazy meals with substituitions | N/A | Priority: Low | AK | Not completed. Moved to future sprint. |  | L | 9
ST-18 | As a group leader I want to be able to create a group for my friend to join | Ability to create groups | 3 | Priority: High | Noah | Completed in sprint 3 | 9 | L | 9
|  |  | Story Point Key | Estimated Hours
|  |  | Small | 2
|  |  | Medium | 5
|  |  | Large | 9
|  |  | Xlarge | 12

## Sprint 2
Project Number | 6
Project Name: | MyKitchen | [7 empty] | Story Point Key | Estimated Hours
Description: | The all-in-one kitchen assistant. You can find recipes, plan meals, create shopping lists, and coordinate with roommates all from the same app! | [7 empty] | Small | 2
Team Members | Levi Carpenter, Akshay Patel, Erick Garcia, Noah Gillespie | [7 empty] | Medium | 5
[9 empty] | Large | 9
Assumes 1 hour per point
Note; This is an example of a "Done" page for Sprint 2. Replace your projects estimates and actuals | [6 empty] | Sprint 2
| Card Front | Card Back | Sprint Number | Priority* | Total Estimated Size (S,M,L) | Total Estimated Size (Points) | Estimated Size (Hours) | Actual Hours |  |  | All of these user stories were incomplete at the end of Sprint 2. Actual Hours were not known
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality>
ST-3 | As a cook, I want to be able to search for recipes so that I can try to cook new things | Search for online recipes | 3 | Priority: Medium | L | 9 | 9 | N/A
ST-8 | As a cook, I would like to be able to upload recipies to the app so that I can store my personal recipies in one place | Ability to upload recipies for personal use on the apps | 4 | Priority: Medium | S | 2 | 2 | N/A
ST-9 | As a college roomate I want to be able to join my roomate in a shared space to look at the groceries we are going to get this week | Ability for roomates to join groups | 3 | Priority: High | XL | 12 | 12 | N/A
ST-11 | As a late night worker, I want to see what meals I have planned for the week on my way home from work so that I will be able to more effeciently pick a meal | Meal viewer | 3 | Priority: High | L | 9 | 9 | N/A
|  |  |  | Sprint 2 |  | Velocity per Sprint | 32 | 0
* It might not conform to the Sprint numbers here, but remains same as your group decided in the initial sprint | [5 empty] | Velocity per Sprint Delta | Velocity per Sprint | 0
[7 empty] | Velocity per Sprint Delta | 0
** Each Sprint needs to be of the same length (for example Sorints 2, 3, … n all must be same duration for this method to be a valid way to calculate velocity).

## Sprint 3
Project Number | 6
Project Name: | MyKitchen | [7 empty] | Story Point Key | Estimated Hours
Description: | The all-in-one kitchen assistant. You can find recipes, plan meals, create shopping lists, and coordinate with roommates all from the same app! | [7 empty] | Small | 2
Team Members | Levi Carpenter, Akshay Patel, Erick Garcia, Noah Gillespie | [7 empty] | Medium | 5
[9 empty] | Large | 9
Assumes 1 hour per point
Sprint 3
| Card Front | Card Back | Sprint Number | Priority* | Assigned to: | Total Estimated Size (S,M,L) | Estimated Size (Hours) | Actual Hours
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality>
ST-1 | As a user, I want to register for a new account so that I can use the app | Registering new accounts | 3 | Priority: High | Levi | L | 9 | 8
ST-2 | As a user, I want to sign into my account so that I can use the app | Sign in to existing accounts | 3 | Priority: High | Levi | M | 5 | 7
ST-3 | As a cook, I want to be able to search for recipes so that I can try to cook new things | Search for online recipes | 3 | Priority: Medium | Levi | L | 9 | 15
ST-5 | As a frequent home cook, I want the app to keep track of my pantry so that I am not buying ingredients I already own | Pantry section | 3 | Priority: High | AK, Completed by Levi | S | 2 | 11
ST-7 | As a shopper, I want my ingredients to be grouped into types so that my shopping trip is more efficient | Grocery list grouping | 3 | Priority: High | Levi | M | 5 | 3
ST-9 | As a college roomate I want to be able to join my roomate in a shared space to look at the groceries we are going to get this week | Ability for roomates to join groups | Started in sprint 3, moved to 4 | Priority: High | Noah | XL | 12 | 10 | WIP
ST-11 | As a late night worker, I want to see what meals I have planned for the week on my way home from work so that I will be able to more effeciently pick a meal | Meal viewer | 3 | Priority: High | Erick | L | 9 | 25
ST-12 | As a home cook, I want to be able to manually add and remove items from my pantry so that the pantry section of the app is always accurate | Manual pantry/personalList additions / removal | 3 | Priority: Medium | AK, Completed by Levi | S | 2 | 12
ST-18 | As a group leader I want to be able to create a group for my friend to join | Ability to create groups | 3 | Priority: High | Noah | L | 9 | 15
[6 empty] | Sprint 3 | 62 | 106
* It might not conform to the Sprint numbers here, but remains same as your group decided in the initial sprint | [6 empty] | Sprint 3 Velocity | 106
[7 empty] | Sprint 3 Velocity Delta | 1.7097
** Each Sprint needs to be of the same length (for example Sorints 2, 3, … n all must be same duration for this method to be a valid way to calculate velocity).

## Sprint 4
Project Number | 6
Project Name: | MyKitchen | [7 empty] | Story Point Key | Estimated Hours
Description: | The all-in-one kitchen assistant. You can find recipes, plan meals, create shopping lists, and coordinate with roommates all from the same app! | [7 empty] | Small | 2
Team Members | Levi Carpenter, Akshay Patel, Erick Garcia, Noah Gillespie | [7 empty] | Medium | 5
[9 empty] | Large | 9
Assumes 1 hour per point
Sprint 4
| Card Front | Card Back | Sprint Number | Priority* | Assigned to: | Total Estimated Size (S,M,L) | Estimated Size (Hours) | Actual Hours
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality>
ST-4 | As a student, I want to be able to share my grocery list with my roomates so that splitting the bill is easier | Grocery list sharing | 4 | Priority: High | Noah/Levi | M | 5 | 19
ST-8 | As a cook, I would like to be able to upload recipies to the app so that I can store my personal recipies in one place | Ability to upload recipies for personal use on the apps | 4 | Priority: Medium | Levi | S | 2 | 15
ST-9 | As a college roomate I want to be able to join my roomate in a shared space to look at the groceries we are going to get this week | Ability for roomates to join groups | 4 | Priority: High | Noah/Levi | XL | 12 | 27.5
ST-10 | As a roommate, I would like to add an item to the grocery list for the house wide grocery list | Ability for roomates to add and edit grocery lists | 4 | Priority: High | Noah/Levi | M | 5 | 17
ST-14 | As a shopper, I want to be able to mark items off of my grocery list, so that I can keep track of what I have already picked up while shopping | Ingredient mark off | 4 | Priority: Medium | Levi | S | 2 | 10
ST-15 | As a cook who plans meals for the week, I want to be able to mark off meals as I cook them so that I know what's left to cook | Mark off cooked meals in meal viewer | 4 | Priority: Medium | Erick | S | 2 | 4
[6 empty] | Sprint 4 | 28 | 92.5
* It might not conform to the Sprint numbers here, but remains same as your group decided in the initial sprint | [6 empty] | Sprint 4 Velocity | 92.5
[7 empty] | Sprint 4 Velocity Delta | 3.3036
** Each Sprint needs to be of the same length (for example Sorints 2, 3, … n all must be same duration for this method to be a valid way to calculate velocity).

## Story Point Velocity Levi
ONE SPREADSHEET FOR EACH STUDENT
Levi
Story Point Velocity - Delta***
Velocity Delta |  |  |  |  | Steps for calculating velocity in hours (Assumes one hour for each point)
1. Enter estimated points from Sprint 3 tab
2. Enter actual points from Sprint 3 tab
3. Divide (2) / (1)
4. Velocity Delta is number of actual points (or hours)* divided by estimated points (or hours)*
Goal is to get Velocity to 1.0 by the time we are done with this class
| Measure* | Sprint 2 | Sprint 3 | Sprint 4 | Key
| 1. Estimated Points (Hours)* | 11 | 32 | 26 | 10% or less miss
| 2. Actual Points (Hours)* | 21 | 56 | 63 | .11 to 1.99 miss
| 3. Actual Hours per Point | 1.9091 | 1.75 | 2.42 | Greater than 2.0 miss
| 4. Velocity Delta* | 1.9091 | 1.75 | 2.42
* For illustration purposes this assumes 2 Hours for Small, 5 Hours for Medium, 9 Hours for Large relative sizing. * In this case one hour equals one story point -- this is for illustration purposes only; seldom are points and hours equal.
** Each Sprint needs to be of the same length (for example Sorints 2, 3, … n all must be same duration for this method to be a valid way to calculate velocity).
*** A perfect velocity delta (Actual divided by Estimated equals 1.0) means you have mastered estimation

## Story Point Velocity Noah
ONE SPREADSHEET FOR EACH STUDENT
Noah
Story Point Velocity - Delta***
Velocity Delta |  |  |  |  | Steps for calculating velocity in hours (Assumes one hour for each point)
1. Enter estimated points from Sprint 3 tab
2. Enter actual points from Sprint 3 tab
3. Divide (2) / (1)
4. Velocity Delta is number of actual points (or hours)* divided by estimated points (or hours)*
Goal is to get Velocity to 1.0 by the time we are done with this class
| Measure* | Sprint 2 | Sprint 3 | Sprint 4 | Key
| 1. Estimated Points (Hours)* | 11 | 12 | 22 | 10% or less miss
| 2. Actual Points (Hours)* | 15 | 25 | 25.5 | .11 to 1.99 miss
| 3. Actual Hours per Point | 1.3636 | 2.0833 | 1.1591 | Greater than 2.0 miss
| 4. Velocity Delta* | 1.3636 | 2.08 | 1.1591
* For illustration purposes this assumes 2 Hours for Small, 5 Hours for Medium, 9 Hours for Large relative sizing. * In this case one hour equals one story point -- this is for illustration purposes only; seldom are points and hours equal.
** Each Sprint needs to be of the same length (for example Sorints 2, 3, … n all must be same duration for this method to be a valid way to calculate velocity).
*** A perfect velocity delta (Actual divided by Estimated equals 1.0) means you have mastered estimation

## Story Point Velocity Erick
ONE SPREADSHEET FOR EACH STUDENT
Erick
Story Point Velocity - Delta***
Velocity Delta |  |  |  |  | Steps for calculating velocity in hours (Assumes one hour for each point)
1. Enter estimated points from Sprint 3 tab
2. Enter actual points from Sprint 3 tab
3. Divide (2) / (1)
4. Velocity Delta is number of actual points (or hours)* divided by estimated points (or hours)*
Goal is to get Velocity to 1.0 by the time we are done with this class
| Measure* | Sprint 2 | Sprint 3 | Sprint 4 | Key
| 1. Estimated Points (Hours)* | 11 | 12 | 2 | 10% or less miss
| 2. Actual Points (Hours)* | 12 | 25 | 8 | .11 to 1.99 miss
| 3. Actual Hours per Point | 1.0909 | 2.0833 | 4 | Greater than 2.0 miss
| 4. Velocity Delta* | 1.09 | 2.08 | 4
* For illustration purposes this assumes 2 Hours for Small, 5 Hours for Medium, 9 Hours for Large relative sizing. * In this case one hour equals one story point -- this is for illustration purposes only; seldom are points and hours equal.
** Each Sprint needs to be of the same length (for example Sorints 2, 3, … n all must be same duration for this method to be a valid way to calculate velocity).
*** A perfect velocity delta (Actual divided by Estimated equals 1.0) means you have mastered estimation

## Story Point Velocity Akshay
ONE SPREADSHEET FOR EACH STUDENT
Akshay
Story Point Velocity - Delta***
Velocity Delta |  |  |  |  | Steps for calculating velocity in hours (Assumes one hour for each point)
1. Enter estimated points from Sprint 3 tab
2. Enter actual points from Sprint 3 tab
3. Divide (2) / (1)
4. Velocity Delta is number of actual points (or hours)* divided by estimated points (or hours)*
Goal is to get Velocity to 1.0 by the time we are done with this class
| Measure* | Sprint 2 | Sprint 3 | Sprint 4 | Key
| 1. Estimated Points (Hours)* | 11 | 4 | 9 | 10% or less miss
| 2. Actual Points (Hours)* | 4 | 7 | 1 | .11 to 1.99 miss
| 3. Actual Hours per Point | 0.36364 | 1.75 | 0.11111 | Greater than 2.0 miss
| 4. Velocity Delta* | 0.36 | 1.75 | 0.11111
* For illustration purposes this assumes 2 Hours for Small, 5 Hours for Medium, 9 Hours for Large relative sizing. * In this case one hour equals one story point -- this is for illustration purposes only; seldom are points and hours equal.
** Each Sprint needs to be of the same length (for example Sorints 2, 3, … n all must be same duration for this method to be a valid way to calculate velocity).
*** A perfect velocity delta (Actual divided by Estimated equals 1.0) means you have mastered estimation

## Burndown Chart (hidden)
Sprint management template |  |  | Author: Rishikesh Parkhe
Number of days | 10
Starting Story points | 120
Ideal burn-rate | 13.3333 | Current Day SP | 112 | 8
Every day updates
Day | Ideal | Actual burnt | Velocity
1 | 120 | 120 | 0
2 | 106.6667 | 110 | 10
3 | 93.3333 | 102 | 8
4 | 80 | 100 | 2
5 | 66.6667 | 98 | 2
6 | 53.3333 | 88 | 10
7 | 40 |  | 88
8 | 26.6667 |  | 0
9 | 13.3333 |  | 0
10 | 0 |  | 0
** Each Sprint needs to be of the same length (for example Sorints 2, 3, … n all must be same duration for this method to be a valid way to calculate velocity).